## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Aleksandra Bratic | 3039067845 | 8 | Tues-Sun
Sue Jones | 555-2567 | 8 | Mon - Fri
Tim Thomas | 555-2243 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Bob Smith
Documentation Developer | Bob Smith
Data Warehouse Developer | Aleksandra Bratic
ETL developer | Sue Jones
Cube Developer | Sue Jones
Report Developer | Sue Jones
Testers | Tim Thomas
Release Manager | Tim Thomas

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Original Data Source
Original Data Source Data
CustomerID | CompanyName | ContactName | ContactTitle | Address | City | Region | PostalCode | Country | Phone | Fax
ALFKI | Alfreds Futterkiste | Maria Anders | Sales Representative | Obere Str. 57 | Berlin | NULL | 12209 | Germany | 030-0074321 | 030-0076545
ANATR | Ana Trujillo Emparedados y helados | Ana Trujillo | Owner | Avda. de la Constitución 2222 | México D.F. | NULL | 5021 | Mexico | (5) 555-4729 | (5) 555-3745
EmployeeID | LastName | FirstName | Title | TitleOfCourtesy | BirthDate | HireDate | Address | City | Region | PostalCode | Country | HomePhone | Extension | Photo | Notes | ReportsTo | PhotoPath
1 | Davolio | Nancy | Sales Representative | Ms. | 1948-12-08 | 1992-05-01 | 507 - 20th Ave. E. Apt. 2A | Seattle | WA | 98122 | USA | (206) 555-9857 | 5467 | Binary Data | Some Notes | 2 | http://accweb/emmployees/davolio.bmp
2 | Fuller | Andrew | Vice President, Sales | Dr. | 1952-02-19 | 1992-08-14 | 908 W. Capital Way | Tacoma | WA | 98401 | USA | (206) 555-9482 | 3457 | Binary Data | Some Notes | NULL | http://accweb/emmployees/fuller.bmp
OrderID | CustomerID | EmployeeID | OrderDate | RequiredDate | ShippedDate | ShipVia | Freight | ShipName | ShipAddress | ShipCity | ShipRegion | ShipPostalCode | ShipCountry
10248 | VINET | 5 | 1996-07-04 | 1996-08-01 | 1996-07-16 | 3 | 32.38 | Vins et alcools Chevalier | 59 rue de l'Abbaye | Reims | NULL | 51100 | France
10249 | TOMSP | 6 | 1996-07-05 | 1996-08-16 | 1996-07-10 | 1 | 11.61 | Toms Spezialitäten | Luisenstr. 48 | Münster | NULL | 44087 | Germany
OrderID | ProductID | UnitPrice | Quantity | Discount
10248 | 11 | 14 | 12 | 0
10248 | 42 | 9.8 | 10 | 0
ProductID | ProductName | SupplierID | CategoryID | QuantityPerUnit | UnitPrice | UnitsInStock | UnitsOnOrder | ReorderLevel | Discontinued
1 | Chai | 1 | 1 | 10 boxes x 20 bags | 18 | 39 | 0 | 10 | 0
2 | Chang | 1 | 1 | 24 - 12 oz bottles | 19 | 17 | 40 | 25 | 0
CategoryID | CategoryName | Description | Picture
1 | Beverages | Soft drinks, coffees, teas, beers, and ales | Binary Data
2 | Condiments | Sweet and savory sauces, relishes, spreads, and seasonings | Binary Data
Original Data Source Design
TABLE_NAME | COLUMN_NAME | DataType | CONSTRAINT_NAME | CONSTRAINT_TYPE | IS_NULLABLE | CHECK_CLAUSE | COLUMN_DEFAULT | Is_Identity
Categories | CategoryID | int | PK_Categories | PRIMARY KEY | NO | NULL | NULL | Yes
Categories | CategoryName | nvarchar(15) | NULL | NULL | NO | NULL | NULL | No
Categories | Description | ntext(1073741823) | NULL | NULL | YES | NULL | NULL | No
Categories | Picture | image(2147483647) | NULL | NULL | YES | NULL | NULL | No
Customers | CustomerID | nchar(5) | PK_Customers | PRIMARY KEY | NO | NULL | NULL | No
Customers | CompanyName | nvarchar(40) | NULL | NULL | NO | NULL | NULL | No
Customers | ContactName | nvarchar(30) | NULL | NULL | YES | NULL | NULL | No
Customers | ContactTitle | nvarchar(30) | NULL | NULL | YES | NULL | NULL | No
Customers | Address | nvarchar(60) | NULL | NULL | YES | NULL | NULL | No
Customers | City | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Customers | Region | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Customers | PostalCode | nvarchar(10) | NULL | NULL | YES | NULL | NULL | No
Customers | Country | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Customers | Phone | nvarchar(24) | NULL | NULL | YES | NULL | NULL | No
Customers | Fax | nvarchar(24) | NULL | NULL | YES | NULL | NULL | No
Employees | EmployeeID | int | PK_Employees | PRIMARY KEY | NO | NULL | NULL | Yes
Employees | LastName | nvarchar(20) | NULL | NULL | NO | NULL | NULL | No
Employees | FirstName | nvarchar(10) | NULL | NULL | NO | NULL | NULL | No
Employees | Title | nvarchar(30) | NULL | NULL | YES | NULL | NULL | No
Employees | TitleOfCourtesy | nvarchar(25) | NULL | NULL | YES | NULL | NULL | No
Employees | BirthDate | datetime | CK_Birthdate | CHECK | YES | ([BirthDate]<getdate()) | NULL | No
Employees | HireDate | datetime | NULL | NULL | YES | NULL | NULL | No
Employees | Address | nvarchar(60) | NULL | NULL | YES | NULL | NULL | No
Employees | City | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Employees | Region | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Employees | PostalCode | nvarchar(10) | NULL | NULL | YES | NULL | NULL | No
Employees | Country | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Employees | HomePhone | nvarchar(24) | NULL | NULL | YES | NULL | NULL | No
Employees | Extension | nvarchar(4) | NULL | NULL | YES | NULL | NULL | No
Employees | Photo | image(2147483647) | NULL | NULL | YES | NULL | NULL | No
Employees | Notes | ntext(1073741823) | NULL | NULL | YES | NULL | NULL | No
Employees | ReportsTo | int | FK_Employees_Employees | FOREIGN KEY | YES | NULL | NULL | No
Employees | PhotoPath | nvarchar(255) | NULL | NULL | YES | NULL | NULL | No
Order Details | OrderID | int | FK_Order_Details_Orders | FOREIGN KEY | NO | NULL | NULL | No
Order Details | OrderID | int | PK_Order_Details | PRIMARY KEY | NO | NULL | NULL | No
Order Details | ProductID | int | FK_Order_Details_Products | FOREIGN KEY | NO | NULL | NULL | No
Order Details | ProductID | int | PK_Order_Details | PRIMARY KEY | NO | NULL | NULL | No
Order Details | UnitPrice | money | CK_UnitPrice | CHECK | NO | ([UnitPrice]>=(0)) | ((0)) | No
Order Details | Quantity | smallint | CK_Quantity | CHECK | NO | ([Quantity]>(0)) | ((1)) | No
Order Details | Discount | real | CK_Discount | CHECK | NO | ([Discount]>=(0) AND [Discount]<=(1)) | ((0)) | No
Orders | OrderID | int | PK_Orders | PRIMARY KEY | NO | NULL | NULL | Yes
Orders | CustomerID | nchar(5) | FK_Orders_Customers | FOREIGN KEY | YES | NULL | NULL | No
Orders | EmployeeID | int | FK_Orders_Employees | FOREIGN KEY | YES | NULL | NULL | No
Orders | OrderDate | datetime | NULL | NULL | YES | NULL | NULL | No
Orders | RequiredDate | datetime | NULL | NULL | YES | NULL | NULL | No
Orders | ShippedDate | datetime | NULL | NULL | YES | NULL | NULL | No
Orders | ShipVia | int | FK_Orders_Shippers | FOREIGN KEY | YES | NULL | NULL | No
Orders | Freight | money | NULL | NULL | YES | NULL | ((0)) | No
Orders | ShipName | nvarchar(40) | NULL | NULL | YES | NULL | NULL | No
Orders | ShipAddress | nvarchar(60) | NULL | NULL | YES | NULL | NULL | No
Orders | ShipCity | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Orders | ShipRegion | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Orders | ShipPostalCode | nvarchar(10) | NULL | NULL | YES | NULL | NULL | No
Orders | ShipCountry | nvarchar(15) | NULL | NULL | YES | NULL | NULL | No
Products | ProductID | int | PK_Products | PRIMARY KEY | NO | NULL | NULL | Yes
Products | ProductName | nvarchar(40) | NULL | NULL | NO | NULL | NULL | No
Products | SupplierID | int | FK_Products_Suppliers | FOREIGN KEY | YES | NULL | NULL | No
Products | CategoryID | int | FK_Products_Categories | FOREIGN KEY | YES | NULL | NULL | No
Products | QuantityPerUnit | nvarchar(20) | NULL | NULL | YES | NULL | NULL | No
Products | UnitPrice | money | CK_Products_UnitPrice | CHECK | YES | ([UnitPrice]>=(0)) | ((0)) | No
Products | UnitsInStock | smallint | CK_UnitsInStock | CHECK | YES | ([UnitsInStock]>=(0)) | ((0)) | No
Products | UnitsOnOrder | smallint | CK_UnitsOnOrder | CHECK | YES | ([UnitsOnOrder]>=(0)) | ((0)) | No
Products | ReorderLevel | smallint | CK_ReorderLevel | CHECK | YES | ([ReorderLevel]>=(0)) | ((0)) | No
Products | Discontinued | bit | NULL | NULL | NO | NULL | ((0)) | No

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Original Source | Source Type | Destination Type
object name | description | source | source type | destination type
DWBroadclothBatch.dbo.factbatch | fact table | Broadcloth.dbo.sales | Table | table
Factbatch.quantityproduced | Measure Column | Broadcloth.dbo.productionbatch | int | int
factbatch.qualityrating | Measure Column | Broadcloth.dbo.productionbatch | numeric(18) | numeric(18)
factbatch.startdate | Measure Column | Broadcloth.dbo.productionbatch | datetime | na
factbatch.estimatedendtime | Measure Column | Broadcloth.dbo.productionbatch | datetime | na
factbatch.actualendtime | Measure Column | Broadcloth.dbo.productionbatch | datetime | na
factbatch.shippingdate | Measure Column | Broadcloth.dbo.shipment | datetime | na
factbatch.productioncost | Measure Column | Broadcloth.dbo.productionbatch | int | int
factbatch.shippingcost | Measure Column | Broadcloth.dbo.shipment | int | int
factbatch.quantityshipped | Measure Column | Broadcloth.dbo.shipment item | int | int
factbatch.orderquantity | Measure Column | Broadcloth.dbo.orderitem | int | int
factbatch.ordersaleprice | Measure Column | Broadcloth.dbo.orderitem | int | int
factbatch.itemID | Key Column | Broadcloth.dbo.item | int | int
factbatch.factoryID | key column | Broadcloth.dbo.factory | int | int
factbatch.shipmentID | key column | Broadcloth.dbo.shipment | int | int
factbatch.workerno | key column | Broadcloth.dbo.Workercheck | int | int
DWBroadclothBatch.dbo.DimShipment | Dimension Table | Broadcloth.dbo.Shipment | table | table
DimShipment.ShipmentKey | Dimension Key Column | na | na | Int
DimShipment.Nation | Dimension Column | Shipment.ShipNation | nvarchar(50) | nvarchar(50)
DimShipment.State | Dimension Column | Shipment.ShipState | nvarchar(20) | nvarchar(20)
DimShipment.City | Dimension Column | Shipment.ShipCity | nvarchar(30) | nvarchar(30)
DimShipment.ShippingCurrency | Dimension Column | Shipment.ShippingCurrency | nvarchar(5) | nvarchar(5)
DWBroadclothBatch.dbo.DimCompliance | Dimension Table | Broadcloth.dbo.Compliance | table | table
DimCompliance.ComplianceKey | Dimension Key Column | na | na | Int
DimCompliance.OverallComplianceRating | Dimension Column | Compliance.OverallRating | numeric(18,0) | decimal(18,0)
DimCompliance.AverageAge | Dimension Column | WorkerCheck.Age | numeric(18,0) | decimal(18,0)
DimCompliance.PercentFemale | Dimension Column | WorkerCheck.Gender | nvarchar(7) | nvarchar(7)
DWBroadclothBath.dbo.DimFactor | dimension table | broadcloth | table | table
DWBroadclothBath.dbo.DimFactory.FactoryKey | Dimension Key Column | na | na | Int
DWBroadclothBath.dbo.DimFactory.Nation | Dimension Column | Broadcloth.dbo.Factory.Nation | nvarchar(50) | nvarchar(50)
DWBroadclothBath.dbo.DimFactory.City | Dimension Column | Broadcloth.dbo.Factory.City | nvarchar(30) | nvarchar(30)
DWBroadclothBath.dbo.DimFactory.GMTDifference | Dimension Column | Broadcloth.dbo.Factory.GMTDifference | numeric(18) | numeric(18)
DWBroadclothBath.dbo.DimFactory.MaxWorkers | Dimension Column | Broadcloth.dbo.Factory.MaxWorkers | int | int
DWBroadclothBath.dbo.DimFactory.BaseCurrency | Dimension Column | Broadcloth.dbo.Factory.BaseCurrency | nvarchar(20) | nvarchar(20)
DWBroadClothBatch.dbo.DimItem | Dimesion Table | Broadcloth.dbo.Item | table | table
DWBroadClothBatch.dbo.DimItem.ItemKey | Dimesnion Key Column | na | na | Int
DWBroadClothBatch.dbo.DimItem.ModelDescription | Dimension Column | Broadcloth.dbo.Model.ModelDescription | nvarchar(250), null | nvarchar(250), null
DWBroadClothBatch.dbo.DimItem.BasePrice | Dimension Column | Broadcloth.dbo.Model.BasePrice | numeric(9,4) | decimal(9,4)
DWBroadClothBatch.dbo.DimItem.ListPrice | Dimension Column | Broadcloth.dbo.Item.ListPrice | numeric(38,4) | decimal(38,4)
DWBroadClothBatch.dbo.DimItem.Color | Dimension Column | Broadcloth.dbo.ColorList.Color | nvarchar(20) | nvarchar(20)
DWBroadClothBatch.dbo.DimItem.ItemSize | Dimension Column | Broadcloth.dbo.Item.ItemSize | numeric(18,0) | decimal(18,0)
DWBroadclothBatch.dbo.Order | Dimension Table | Broadcloth.dbo.Order | Table | Table
Order.OrderKey | Dimension Key | na | na | Int
Order.DeliveryNation | Dimension Column | Order.DeliveryNation | nvarchar(50) | nvarchar(50)
Order.DeliveryState | Dimension Column | Order.DeliveryState | nvarchar(20) | nvarchar(20)
Order.DeliveryCity | Dimension Column | Order.DeliveryCity | nvarchar(30) | nvarchar(30)
Order.PriceAdjustment | Dimension Column | Order.PriceAdjustment | numeric(38,4) | decimal(38,4)
Order.Currency | Dimension Column | Order.OrderCurrency | nvarchar(5) | nvarchar(5)

## Sheet1
object name | description | source | source type | destination type
DWBroadclothBatch.dbo.factbatch | fact table | Broadcloth.dbo.sales | Table | table
Factbatch.quantityproduced | Measure Column | Broadcloth.dbo.productionbatch | int | int
factbatch.qualityrating | Measure Column | Broadcloth.dbo.productionbatch | numeric(18) | numeric(18)
factbatch.startdate | Measure Column | Broadcloth.dbo.productionbatch | datetime | na
factbatch.estimatedendtime | Measure Column | Broadcloth.dbo.productionbatch | datetime | na
factbatch.actualendtime | Measure Column | Broadcloth.dbo.productionbatch | datetime | na
factbatch.shippingdate | Measure Column | Broadcloth.dbo.shipment | datetime | na
factbatch.productioncost | Measure Column | Broadcloth.dbo.productionbatch | int | int
factbatch.shippingcost | Measure Column | Broadcloth.dbo.shipment | int | int
factbatch.quantityshipped | Measure Column | Broadcloth.dbo.shipment item | int | int
factbatch.orderquantity | Measure Column | Broadcloth.dbo.orderitem | int | int
factbatch.ordersaleprice | Measure Column | Broadcloth.dbo.orderitem | int | int
factbatch.itemID | Key Column | Broadcloth.dbo.item | int | int
factbatch.factoryID | key column | Broadcloth.dbo.factory | int | int
factbatch.shipmentID | key column | Broadcloth.dbo.shipment | int | int
factbatch.workerno | key column | Broadcloth.dbo.Workercheck | int | int
DWBroadclothBatch.dbo.DimShipment | Dimension Table | Broadcloth.dbo.Shipment | table | table
DimShipment.ShipmentKey | Dimension Key Column | na | na | Int
DimShipment.Nation | Dimension Column | Shipment.ShipNation | nvarchar(50) | nvarchar(50)
DimShipment.State | Dimension Column | Shipment.ShipState | nvarchar(20) | nvarchar(20)
DimShipment.City | Dimension Column | Shipment.ShipCity | nvarchar(30) | nvarchar(30)
DimShipment.ShippingCurrency | Dimension Column | Shipment.ShippingCurrency | nvarchar(5) | nvarchar(5)
DWBroadclothBatch.dbo.DimCompliance | Dimension Table | Broadcloth.dbo.Compliance | table | table
DimCompliance.ComplianceKey | Dimension Key Column | na | na | Int
DimCompliance.ConditionCategory | Dimension Column | Compliance.ConditionCategory | nvarchar(50) | nvarchar(50)
DimCompliance.OverallComplianceRating | Dimension Column | Compliance.OverallRating | numeric(18,0) | decimal(18,0)
DimCompliance.Age | Dimension Column | Compliance.Age | numeric(18,0) | decimal(18,0)
DimCompliance.AgeDocuments | Dimension Column | Compliance.AgeDocuments | nvarchar(150) | nvarchar(150)
DimCompliance.Gender | Dimension Column | Compliance.Gender | nvarchar(7) | nvarchar(7)
DWBroadclothBath.dbo.DimFactor | dimension table | broadcloth | table | table
DWBroadclothBath.dbo.DimFactory.FactoryKey | Dimension Key Column
DWBroadclothBath.dbo.DimFactory.Nation | Dimension Column | Broadcloth.dbo.Factory.Nation | nvarchar(50) | nvarchar(50)
DWBroadclothBath.dbo.DimFactory.City | Dimension Column | Broadcloth.dbo.Factory.City | nvarchar(30) | nvarchar(30)
DWBroadclothBath.dbo.DimFactory.GMTDifference | Dimension Column | Broadcloth.dbo.Factory.GMTDifference | numeric(18) | numeric(18)
DWBroadclothBath.dbo.DimFactory.MaxWorkers | Dimension Column | Broadcloth.dbo.Factory.MaxWorkers | int | int
DWBroadclothBath.dbo.DimFactory.BaseCurrency | Dimension Column | Broadcloth.dbo.Factory.BaseCurrency | nvarchar(20) | nvarchar(20)
DWBroadClothBatch.dbo.DimItem | Dimesion Table
DWBroadClothBatch.dbo.DimItem.ItemKey | Dimesnion Key Column
DWBroadClothBatch.dbo.DimItem.ModelDescription | Dimension Column | Broadcloth.dbo.Model.ModelDescription | nvarchar(250), null | nvarchar(250), null
DWBroadClothBatch.dbo.DimItem.BasePrice | Dimension Column | Broadcloth.dbo.Model.BasePrice | numeric(9,4) | decimal(9,4)
DWBroadClothBatch.dbo.DimItem.ListPrice | Dimension Column | Broadcloth.dbo.Item.ListPrice | numeric(38,4) | decimal(38,4)
DWBroadClothBatch.dbo.DimItem.Color | Dimension Column | Broadcloth.dbo.ColorList.Color | nvarchar(20) | nvarchar(20)
DWBroadClothBatch.dbo.DimItem.ItemSize | Dimension Column | Broadcloth.dbo.Item.ItemSize | numeric(18,0) | decimal(18,0)

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Type | Description